| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1403-04 |
| Month: | August 2004 |

- Program Status

Program Description

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA’s progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,273,152 | $4,522 | 0% | $10,103 | 1% | $47,232 | 4% | $57,335 | 5% | $1,263,049 |
| Admin | $126,899 | $4,522 | 4% | $10,103 | 8% | $12,399 | 10% | $22,502 | 18% | $116,796 |
| Marketing | $18,575 |  |  |  |  | $101 | 1% | $101 | 1% | $18,575 |
| DI | $1,066,896 |  |  |  |  | $34,732 | 3% | $34,732 | 3% | $1,066,896 |
| EM&V | $60,781 |  |  |  |  |  |  |  |  | $60,781 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the VCREA to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE receives this information, the costs now shown in the committed column will be reported in the supporting workbook.

    - Energy Effects

| Energy Effects | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,618 |  |  |  |  |  |  |  |  | 1,618 |
| Annual kWh | 6,432,343 |  |  |  |  |  |  |  |  | 6,432,343 |
| Lifecyc kWh | 97,593,078 |  |  |  |  |  |  |  |  | 97,593,078 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Conduct at least 6 sessions for businesses | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 6 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Promote VCEEC resources and energy efficiency information at 20 community events or more. | 20 | 0 | 0% | 1 | 5% | 0 | 0% | 1 | 5% | 19 |
| Respond to every customer inquiry within 48 hours. |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Reduce Energy Consumption in Major facilities of VCREA member agencies by 8 % |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Reduce peak demand in major facilities of VCREA member agencies by 5% or more |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |

  - Activities/Accomplishments

1.2.1	Administrative -

- No significant activities

    - Marketing -

- The VCERC was promoted in three local publications of the “Flash Trash” publication for fall quarter distribution (Cities of Ventura, Fillmore and Camarillo).  Copies of publication attached.

    - Direct Implementation –

Significant progress was made toward the first training events scheduled for September 22 and 23 in conjunction with the World Affairs Council of Ventura County event entitled “Energy Choices and Environmental Challenges.” The two training sessions will focus on general energy efficiency for commercial and residential customers.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

The VCERC continued discussions with KEMA-Xenergy regarding the potential of offering the EEGOV Business Energy Services (B.E.S.T.) Team Program to cities within Ventura and initiated discussions with EnSave Energy Performance, Inc. regarding integrating the California Multi Measure Farm Program into Agricultural Training Program.

- Changes to Subcontractors or Staffing

XXXXX joined the VCERC staff as Project Manager in a fill-time capacity on August 15, 2004.

- Additional Items

None